## Sheet1
DATE:17-09-2023
Air Purifier
WORKING:	ISSUES:	CONCLUSION:
We have written code on i2c touch on sample program .	We have worked on i2c touch on development it working well in ssb board.	From our end . code is working on ssb board.
We tested on the threshold value on 2th ,3th ,4th ,5th on i2c touch .	We have issues on the custom board .	when we are working on the custom we are getting issuess only.
On the meeting client confirm that .we should work on the 3 rd threshold value.	When we are testing on the custom board we have the touch issues>>> we worked on totally 12 levels of testing by change the threshold vales 2 to 12 values.	so we felt that source code of air purifier is working well .
Within a week we completed our integeration on i2c touch with 5 values.	when we working on 3rd to 7rd values threshold then it is totally mallfunction .touch didn"t work on the custom board.	we are waiting client new boards
We tested on the smart switch board on develpomemt board we got peferct working logs.	when we got approval from client. we removed the wifi panel which like plastic material .
After meeting they decided that they want threshold value 3rd we fix it.	Then we working on directly on the custom with the i2c touch by the values of 2th to 10th still its in mallfunction .
We haven"t tested the code of buzzer and remote functions.	leds are not working on the board.
We have both code with us .	power touch led is not working
	when we are touch the pad3 .then pad4 leds are coming .
	when we touch on the pad1 ,pad2,pad3,pad4,pad5 .values are getting differently due to touch issues.from 2th to 10th threshold values.
	when we working on the example code of i2c touch board .same issues we are getting.